## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Parag Ramhari Jadhav
PROJECT NAME: | Career Path Predictor
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 29-Jun-2025
Purpose of Document | This Lessons Learnt Log has been prepared as part of the Career Path Predictor project, developed under the Industry Academia Community programme. The project involved building a machine learning-based web application that predicts the most suitable tech job role for a user based on their skills, interests, and personal traits, using an ensemble of four models — Random Forest, XGBoost, LightGBM, and CatBoost — trained on the PS2 career survey dataset. This document captures key lessons encountered during data preprocessing, model training, feature engineering, UI development, and deployment, with the aim of helping future interns and project teams avoid similar challenges and adopt better practices from the outset.
The insights recorded here reflect real events observed across the project lifecycle, covering areas such as data quality issues, model integration challenges, environment compatibility problems, and user experience gaps. Each lesson includes early warning signs, recommendations, and the actions taken, serving as a practical reference for anyone working on similar ML-powered application projects within the Industry Academia Community.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Predictor
PROJECT ID | ML-PROJ-2025-01
PROJECT MANAGER | Student Intern
PROJECT SPONSOR | Industry Mentor / Academic Guide
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 01-Jun-2025 | Dataset had inconsistent categorical values (mixed case, extra spaces) causing label encoding mismatches across models. | Data Quality | Yes | Apply a standardised preprocessing pipeline (strip + lowercase) before encoding; validate unique values per column after cleaning. | Added a data cleaning function that normalises all string columns before encoding; re-trained all four models on the cleaned data. | Intern / Data Engineer | Solved | Issue discovered during initial model training when CatBoost and LightGBM returned different feature sets.
2 | 05-Jun-2025 | LightGBM required underscore-separated feature names while Random Forest, XGBoost, and CatBoost used space-separated names, causing prediction failures at runtime. | Technical / Integration | Yes | Build separate feature-vector functions per model family and store feature name formats alongside saved model artefacts. | Created build_feature_vector_lgbm() and build_feature_vector_standard() helpers; added model-name branching in predict_single(). | Intern / ML Developer | Solved | Caused silent wrong predictions before the branching logic was introduced.
3 | 08-Jun-2025 | Single-model confidence was misleading for edge cases where the predicted role had < 55% probability. | Model Performance | No | Introduce an ensemble (average of all four model probabilities) as the default; show individual model breakdowns for transparency. | Implemented Ensemble (All Models) as the default option in the UI; added a confidence bar and top-3 alternatives panel. | Intern / ML Developer | Solved | Ensemble improved perceived reliability; flagged for further improvement with a larger dataset.
4 | 12-Jun-2025 | Multi-page form with no validation allowed users to reach the prediction step with incomplete inputs, causing KeyError crashes in the feature builder. | UX / Validation | Yes | Validate all required fields before advancing each wizard step; surface a styled error message listing missing fields. | Added per-step validation lists (errors_2, errors_3); rendered a red-styled validation_error() banner and blocked the Next button on failure. | Intern / UI Developer | Solved | UX testing revealed that radio buttons without a default selection returned None, which also needed handling.
5 | 15-Jun-2025 | Joblib model files were not version-pinned in requirements.txt; a newer scikit-learn version on the deployment machine caused joblib.load() to fail with a deserialization error. | Deployment / Environment | No | Pin all library versions in requirements.txt; document the Python version and OS used for training; consider re-serialising models on the target environment. | Pinned scikit-learn==1.5.2, xgboost==2.1.4, lightgbm==4.5.0, catboost==1.2.8, and joblib==1.5.2 in requirements.txt. | Intern / DevOps | Solved | Highlighted the importance of training/serving environment parity for ML projects.
6 | 18-Jun-2025 | Course recommendations were hardcoded per job role with no dynamic personalisation based on the user's declared skill gaps. | Feature Completeness | No | In future iterations, cross-reference user skill ratings against a course-skills mapping to surface the most relevant courses first. | Logged as a backlog item; current release retains static recommendations as a baseline; tagged for v2 enhancement. | Intern / Product | Pending | A skills-gap matrix would require an additional dataset linking courses to competency levels.
7 | 22-Jun-2025 | Streamlit session_state was not initialised before widget rendering on first load, causing AttributeError on rapid page refresh. | Technical / Frontend | Yes | Always initialise all required session_state keys at the top of main() before any widget is rendered. | Added guard blocks (if "wizard_step" not in st.session_state) for all session state variables at the start of main(). | Intern / UI Developer | Solved | Standard Streamlit best practice; documented in inline code comments for future maintainers.