## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Career Path Predictor
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-06-16
EXPECTED COMPLETION DATE | 2026-06-26
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To build a Machine Learning-based web application that predicts the most suitable tech job role for a student from 12 possible career paths, based on 20 input attributes covering skills, certifications, interests, and personal traits. The system uses an ensemble of four ML models — Random Forest, XGBoost, LightGBM, and CatBoost — trained on 6,901 student records from the PS2_Dataset.csv, and is deployed as an interactive 3-step wizard web application using Streamlit.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Manual career counseling is time-consuming, inconsistent, and cannot scale to serve thousands of students simultaneously. An ML-powered ensemble system can analyse student profiles across 20 skill dimensions — encoded into 89 features — and instantly recommend the best-fit career from 12 tech roles, along with confidence scores and tailored course recommendations, enabling scalable, unbiased, and data-driven career guidance.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | 1. Train, tune, and evaluate four ML models: Random Forest, XGBoost, LightGBM, and CatBoost. 2. Implement an ensemble prediction mode that averages probabilities across all four models. 3. Build an interactive 3-step wizard Streamlit web application with per-step input validation. 4. Display prediction results with confidence bars, all-model breakdown, top-3 alternatives, and role-specific course recommendations. 5. Deploy the application publicly on Streamlit Community Cloud.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Four trained and saved ML model files: best_random_forest_model.joblib, best_xgboost_model.joblib, lightgbm_model.joblib, catboost_model.joblib. 2. Interactive Streamlit web application (career_predictor_app.py) with 3-step wizard UI. 3. Pinned dependency file (requirements.txt) with scikit-learn 1.5.2, xgboost 2.1.4, lightgbm 4.5.0, catboost 1.2.8, pandas 2.2.3, numpy 1.26.4, joblib 1.5.2. 4. Project Report and README.md documentation. 5. All deliverable documents (SRS, WBS, RAID Log, Lessons Learnt Log, Requirement Elicitation Questionnaire, Project Charter).
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Data exploration and EDA on PS2_Dataset.csv (6,901 records, 20 columns); data preprocessing and one-hot encoding (20 raw features → 89 encoded features); training and hyperparameter tuning of four ML models (Random Forest, XGBoost, LightGBM, CatBoost); ensemble prediction via probability averaging; model serialisation with joblib; 3-step Streamlit wizard UI development with input validation, confidence visualisation, model breakdown panel, top-3 alternatives, and course recommendation cards; Streamlit Community Cloud deployment.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Real-time data collection from students; integration with university or placement databases; mobile app development; AWS/Azure/GCP cloud infrastructure; user authentication or login system; persistent storage of user predictions; dynamic course recommendation via external APIs; deep learning model integration.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 intern (chetan katkar).
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Python 3.x, VS Code, Jupyter Notebook, scikit-learn 1.5.2, XGBoost 2.1.4, LightGBM 4.5.0, CatBoost 1.2.8, pandas 2.2.3, numpy 1.26.4, joblib 1.5.2, Streamlit, GitHub, Streamlit Community Cloud (free hosting).
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | All tools used are free/open-source. No monetary cost.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Tushar Topale (Sponsor), Harshada Topale (PM), Intern (chetan katkar)
END CUSTOMER (Mention the client name.) | Students seeking data-driven career guidance
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. LightGBM requires underscore-separated feature names while other models use space-separated names — misalignment causes runtime prediction errors. 2. The 20 raw dataset columns expand to 89 one-hot encoded features; any mismatch between training and inference feature vectors causes silent wrong predictions. 3. Library version incompatibility between training and deployment environments can cause joblib model deserialisation failures. 4. Dataset predictive signal may be limited, affecting ensemble confidence scores for certain career roles.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. The PS2_Dataset.csv (6,901 records) is complete and usable without external data sources. 2. All four ML models (Random Forest, XGBoost, LightGBM, CatBoost) are pre-trained and saved as .joblib files before app deployment. 3. Python and all pinned libraries in requirements.txt are compatible with the development and deployment machines. 4. Streamlit Community Cloud will remain free and available for deployment throughout the project lifecycle.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. ~14-day project timeline from start to closure. 2. Single team member (1 intern). 3. Limited exclusively to the provided PS2_Dataset.csv — no additional data collection. 4. All tools and libraries must be free and open-source. 5. Model files must be self-contained and loadable via joblib without retraining at runtime.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 2026-06-17
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 2026-06-18
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-06-20
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-06-26
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 2026-06-27
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 2026-06-27
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 2026-06-30