## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 6 | 0 | 0 | 0 | 1 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Career Path Prediction & Guidance System |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 4 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 3 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2026-06-29 | Project Team Lead: | Parag Jadhav |  |  | Dependency | 3 | 0 | 0 | 2 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 16 |  |  |  |  | 3
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
10 | Risk | Dataset class imbalance across 12 career roles may bias model predictions toward majority classes | Minority career roles (e.g., Security Analyst, Business Analyst) may be under-predicted, skewing career guidance for students in those fields | Analysed class distribution using value_counts(). Imbalance confirmed but marginal (~8% variance). Applied class_weight='balanced' in Random Forest as a precaution. | Intern (Parag) | Moderate |  | Closed | High
3 | Risk | Low model accuracy due to weak feature-target correlation in dataset | Model predictions may not be reliable for real-world career guidance | Documented as a dataset limitation. Performed 5 feature engineering experiments to verify. Added disclaimer in the app. | Intern (Parag) | High |  | Closed | Issue
5 | Risk | Combined model file size (~30 MB for 4 .joblib files: RF, XGBoost, LightGBM, CatBoost) may slow Streamlit Community Cloud cold starts | First load after inactivity may take 10–20 seconds on free-tier deployment | Acceptable for internship scope. Used @st.cache_resource to cache all 4 models after first load. For production, model compression or ONNX export could be considered. | Intern (Parag) | Low |  | Closed
6 | Assumption | PS2_Dataset.csv contains sufficient predictive signal | Feature analysis proved this assumption was incorrect — 13/19 features have zero mutual information with target | Documented finding. Proceeded with model training to demonstrate complete ML pipeline. | Intern (Parag) | High |  | Closed | Open
7 | Assumption | All Python libraries (scikit-learn, XGBoost, LightGBM, CatBoost, Streamlit) will be compatible with the deployment Python version (3.11+) | All 4 model libraries installed and ran successfully without version conflicts on Streamlit Community Cloud | No action needed. Verified compatibility by successful model loading and prediction on deployment. | Intern (Parag) | Negligible |  | Closed | Closed
8 | Dependency | Streamlit Community Cloud for deployment | Required for public access to the app | Free tier is sufficient. No cost involved. | Intern (Parag) | Moderate |  | Open
9 | Issue | SVM models (best_svm_model, svm_linear_model) included in initial app but had no predict_proba(); used decision_function() with softmax approximation | Pseudo-probabilities from softmax-normalised decision scores were less calibrated than true probabilities, reducing ensemble reliability | Removed both SVM models entirely from the app. Ensemble now uses only the 4 models with native predict_proba(): RF, XGBoost, LightGBM, CatBoost. | Intern (Parag) | Moderate |  | Closed | Critical
11 | Risk | Overfitting risk in CatBoost model due to small unique label count (12 classes) relative to 6,901 records | Model may memorise training patterns rather than generalise, leading to inflated training accuracy vs lower test accuracy | Evaluated train vs test accuracy gap. Gap was within 4% threshold. Used early stopping rounds and depth=6 to regularise the model. | Intern (Parag) | Low |  | Closed | Moderate
12 | Assumption | User inputs from the Streamlit form will always fall within the training distribution of the dataset | If a user selects rare combinations of features (e.g., all 0 ratings), the model may output low-confidence or unexpected predictions | Added confidence percentage display and top-3 alternative roles in the results page so users can assess prediction reliability themselves. | Intern (Parag) | Low |  | Closed | Low
13 | Issue | CatBoost model uses feature_names_ attribute (not feature_names_in_) unlike scikit-learn compatible models | Calling model.feature_names_in_ on CatBoost raised AttributeError, breaking the feature vector construction step | Added a model-name conditional check: CatBoost uses model.feature_names_ while RF, XGBoost, and LightGBM use model.feature_names_in_.tolist(). | Intern (Parag) | High |  | Closed | Negligible
14 | Risk | Streamlit session_state may reset unexpectedly on page refresh, causing loss of user's wizard progress | User would lose all entered form data and be forced to restart the 3-step wizard from scratch | Documented as a known Streamlit limitation. Added a 'Start Over' button on the results page for intentional resets. No mitigation available for browser refresh loss. | Intern (Parag) | Low |  | Open
15 | Dependency | GitHub repository must remain public for Streamlit Community Cloud to auto-deploy the app | If repository is made private, the deployment pipeline breaks and the app goes offline | Maintained repository as public throughout the internship period. Sensitive data (model files) uploaded via Streamlit file path, not committed to Git. | Intern (Parag) | Moderate |  | Open
16 | Assumption | One-hot encoding column order generated at inference time will exactly match the column order seen during model training | Column order mismatch would cause models to receive wrong feature values per column, producing completely wrong predictions without any explicit error | Extracted feature_names_in_ / feature_names_ directly from each saved model object and used that ordering explicitly when building the DataFrame — no separate encoding step. | Intern (Parag) | High |  | Closed
17 | Issue | LightGBM predict_proba() returns a 1D array instead of 2D when only one sample is passed in certain configurations | Indexing proba[0] raised IndexError in edge cases during development, breaking the single-sample prediction flow | Ensured input is always passed as a single-row DataFrame (not a Series or plain array). Verified output shape with assert len(proba.shape)==2 before indexing. | Intern (Parag) | Moderate |  | Closed
18 | Risk | Hyperparameter tuning via RandomizedSearchCV was computationally expensive, risking project timeline overrun | Extended tuning sessions (30–60 min per model) on a local machine could delay model finalisation and app development phases | Limited n_iter to 30 for RandomizedSearchCV and used n_jobs=-1 for parallel execution. Tuning was completed within the planned 3-day model development window. | Intern (Parag) | Moderate |  | Closed
19 | Dependency | joblib serialisation version must match between training environment and deployment environment | Models trained on a newer joblib version may fail to load on Streamlit Cloud if the pinned requirements.txt specifies an older version | Captured exact joblib version from training environment using pip freeze and pinned it in requirements.txt. Verified successful model loading on first deployment. | Intern (Parag) | High |  | Closed
20
21
22
23
24