## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Chetan Katkar
Document Created On: | 2026-06-25
Version: | 1

## Project Schedule
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Predictor
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | ML-powered Career Prediction Web Application (4-Model Ensemble)
PROJECT SCOPE
PROJECT START DATE | 2026-06-16
PROJECT END DATE | 2026-06-30
OVERALL PROGRESS | Completed
SL NO | TASK NAME | START DATE | END DATE | DURATION IN DAYS | STATUS
| 1 Initiation (Requirement Gathering) | 2026-06-16 | 2026-06-17 | 2
| 1.1 Setup development environment | 2026-06-16 | 2026-06-16 | 1 | COMPLETED
| 1.2 Install Python libraries | 2026-06-16 | 2026-06-17 | 2 | COMPLETED
| 1.3 Create project folder structure | 2026-06-17 | 2026-06-17 | 1 | COMPLETED
| 2 Planning & Data Exploration | 2026-06-17 | 2026-06-18 | 2
| 2.1 Load and inspect dataset | 2026-06-17 | 2026-06-17 | 1 | COMPLETED
| 2.2 Categorical EDA | 2026-06-17 | 2026-06-17 | 1 | COMPLETED
| 2.3 Numerical EDA and visualizations | 2026-06-18 | 2026-06-18 | 1 | COMPLETED
| 3 Design (Data Preprocessing) | 2026-06-19 | 2026-06-20 | 2
| 3.1 Data cleaning (nulls, duplicates, whitespace) | 2026-06-19 | 2026-06-19 | 1 | COMPLETED
| 3.2 Encode binary and ordinal features | 2026-06-19 | 2026-06-19 | 1 | COMPLETED
| 3.3 Encode complex categorical features | 2026-06-19 | 2026-06-19 | 1 | COMPLETED
| 3.4 Train/test split (80/20 stratified) | 2026-06-20 | 2026-06-20 | 1 | COMPLETED
| 4 Development (Model Training & App) | 2026-06-20 | 2026-06-26 | 7
| 4.1 Train Random Forest | 2026-06-20 | 2026-06-20 | 1 | COMPLETED
| 4.2 Train XGBoost | 2026-06-20 | 2026-06-20 | 1 | COMPLETED
| 4.3 Train LightGBM | 2026-06-21 | 2026-06-21 | 1 | COMPLETED
| 4.4 Train CatBoost | 2026-06-22 | 2026-06-22 | 1 | COMPLETED
| 4.5 Model evaluation and comparison (accuracy, F1-score) | 2026-06-23 | 2026-06-23 | 1 | COMPLETED
| 4.6 Hyperparameter tuning (RandomizedSearchCV) | 2026-06-23 | 2026-06-24 | 1 | COMPLETED
| 4.7 Save final models (.joblib) per algorithm | 2026-06-24 | 2026-06-24 | 1 | COMPLETED
| 4.8 Build Streamlit UI (3-step wizard) | 2026-06-25 | 2026-06-26 | 2 | COMPLETED
| 4.9 Connect ensemble logic to UI | 2026-06-26 | 2026-06-26 | 1 | COMPLETED
| 5 Testing | 2026-06-26 | 2026-06-27 | 2
| 5.1 Testing and bug fixing | 2026-06-26 | 2026-06-27 | 2 | COMPLETED
| 6 Deployment | 2026-06-27 | 2026-06-27 | 1
| 6.1 Deploy to Streamlit Cloud | 2026-06-27 | 2026-06-27 | 1 | COMPLETED
| 7 Closure (Documentation) | 2026-06-28 | 2026-06-30 | 3
| 7.1 Write README.md | 2026-06-28 | 2026-06-28 | 1 | COMPLETED
| 7.2 Fill deliverable documents | 2026-06-28 | 2026-06-30 | 3 | COMPLETED
| 7.3 Create final presentation | 2026-06-30 | 2026-06-30 | 2 | COMPLETED
| 7.4 Final review and submission | 2026-06-30 | 2026-06-30 | 1 | COMPLETED